## Sheet1
User Story | Acceptance Criteria | Owner | Estimate (hrs.) | Actual (hrs.)
Sprint 1
Comparison of previous interfaces with our proposed interface | Find drawbacks & implement in new | Sakshi | 2 | 2
Create a prototype of interface - Gator companion | Design a page | Anushka | 4 | 5
Conducted a focus group | Collect people to study for feedbacks | Richa | 3 | 4
Evaluated feedbacks suggestions. | Extract feedbacks indicating change or upgradation | Sakshi | 5 | 6
Incorporated the suggested features in the website | HTML pages | Anushka | 3 | 4
Sprint 2
Add login feature and password for access | HTML pages for a new login and the next page | Sakshi | 1 | 1
Find algorithms for entries matching | Algorithms for nearest match from options | Richa | 5 | 5
Applied weighted algorithms to perform matching | Assign values of the weighted algorithms | Richa | 3 | 4
Started with the front-end | Html page. | Sakshi | 4 | 5
Learnt php | From videos and lectures | Anushka | 7 | 7
Incorporated the html pages and did back-end | Back-end coding on php | Anushka | 5 | 5
Sprint 3
Added terms and condition for Security | Various Terms and Agreement Condition | Sakshi | 2 | 2
Work done on consent and IRB form | Forms made | Richa | 2 | 2
Created feedback form | Qualtrics Survey questions. | Richa | 4 | 5
Completed Database for storage of the user's details. | My SQL connections with php | Anushka | 5 | 5
Sprint 4
Online hosting | www. webhost000. com - host | Richa | 3 | 4
Conducted User studies of the final interface | Presentation successfully implemented | Sakshi | 5 | 5
Added 'suggested places' as a new tab | Take various pictures of tourism spots | Sakshi | 4 | 4
Refined questions and implemented the table on front end | My SQL, php and host connection | Sakshi | 7 | 7
Evaluated Feedbacks and completion | Surveys- feedback | Anushka | 4 | 4
Made youtube video | Showing the whole interface | Richa | 3 | 3
TOTAL HOURS |  |  | 81 | 89